# ANNEX 2

# ASSEMBLY PARLIAMENTARY SERVICE: RACE EQUALITY ACTION PLAN 2005-2008

# 1.	Background

This report is an overview of progress made in implementing the objectives set out in the Assembly Parliamentary Service’s Race Action Plan for Race Equality during March 2006 and April 2007.

The Assembly Parliamentary Service is committed to achieving the actions in the Assembly’s Race Equality Scheme which are relevant to its functions and staff.  This Action Plan should be read in conjunction with the Scheme which can be found here www.wales.gov.uk/themesraceequality/index.htm

The APS has six functions.  This plan sets out the specific actions that APS will undertake to promote race equality in each of its functions.

In August 2004, the APS assessed the relevance of all of its functions to the general duty of the Race Relations (Amendment) Act 2000.  Each function was then classified using the system contained in Appendix D of the Race Equality Scheme.  The full set of classifications is contained in Appendix B of the Assembly Race Equality Scheme.  Below is a summary of the ratings for APS.

| Function: | Classification: |
| --- | --- |
| Strategic Management | High |
| Formal Proceedings Support | Medium |
| Information and Advice | Medium |
| Facilities and Services | Medium |
| Public Information and Education | Medium |
| Human Resources | High |

# Timetable for further action

As part of the assessment process, the APS has identified further action that it needs to take to promote race equality.  These specific actions are set out on pages 3-21.

# Objectives

The objectives of the Plan are to:

- provide and promote good quality services for all ethnic groups;

- increase awareness of the Assembly among minority ethnic people;

- foster the promotion of race equality in the work of the National Assembly; and

- ensure full compliance with the Government of Wales Act 1998, namely:

Section 48 (The Assembly shall make appropriate arrangements with a view to securing that its business is conducted with due regard to the principle that there should be equality of opportunity for all people); and

Section 120 (The Assembly shall make appropriate arrangements with a view to securing that its functions are exercised with due regard to the principle that there should be equality of opportunity for all people).

4. Future Race Equality Objectives

The Assembly Commission is developing a Single Equality Scheme and Action Plan which will subsume any outstanding race equality objectives contained in this update report.

| Function: Strategic Management | Classification: High |
| --- | --- |
| Objectives: to ensure implementation of the APS Action Plan as a whole; to demonstrate clear leadership and ownership of the Plan by senior management; to give due consideration to minority ethnic issues in senior management team meetings; to give due consideration to minority ethnic issues in planning and reporting Assembly activities; and to encourage consideration of the needs of minority ethnic people in all relevant Assembly activities. |
| Actions | Date | Lead | Performance Measures |
| Set up an APS Equality Steering Group | To be established May 2005 | Clerk/Equality Champion | The terms of reference for the group were extended in 2006 to reconstitute it as the APS Equality Steering Group. The Group consists of equality leads that monitor progress in implementing the Race Equality Action Plan. It met three times between April 2006 and March 2007 and its purpose is: to monitor and evaluate progress on APS statutory equality plans and reports; and act as a catalyst and discussion forum for equal opportunities issues in APS. |
| Build capacity for a dedicated Equality Champion | To be appointed May 2005 | Clerk/Equality Champion | Denise Rogers was appointed as APS Equality Champion, working full time on an equality capacity building project between November 2005 and November 2006 and reported to the Clerk at regular intervals. Third Assembly Update From December 2006 – current: Holly Pembridge (Corporate Unit) has taken forward the role and is establishing an Equalities Team in the Corporate Unit. |
| Ensure that race equality is a quarterly standing item on senior management meeting agendas | From May 2005 | Clerk | Third Assembly Update Equalities work is now planned through the Corporate Unit and the Equalities Team liaises with the Executive Board on a regular basis. |
| Ensure that information about progress with the Race Equality Action Plan is reported to the House Committee and included in relevant House Committee and APS reports | From May 2005 | Clerk | The Clerk produced an annual report of arrangements to promote equality of opportunity, incorporating race equality elements in the financial year 2005-06 which was presented at Equality of Opportunity Committee – 25 October 2006. House Committee considered the report on implementing the race equality actions on 13 July 2006. |

| Function: Formal Proceedings Support | Classification: Medium |
| --- | --- |
| Objectives: greater awareness of minority ethnic issues amongst Members; and improved scrutiny of Assembly Departmental Race Equality Plans |
| Actions | Date | Lead | Performance Measures |
| The Equality of Opportunity Committee Clerk will draw up a checklist, in consultation with Equality of Opportunity Committee standing invitees, for committees to use to assess their handling of equality issues (in line with recommendation 27 of Equality of Opportunity Committee report on Mainstreaming Equality). | By and from April 2005 | Clerk to the Equality of Opportunity Committee | Prior to the production of the checklist, a seminar was held on 10 Feb 2005 with Clerks and Equality of Opportunity Committee standing invitees (including the CRE) to identify ways of assisting Committee Chairs to mainstream equality considerations into Forward Work Programmes and Agendas. A checklist was produced and distributed to Committee Clerks and Chairs on 11 July 2005, after consultation with Standing Invitees (including the Commission for Racial Equality). The checklist draws attention to the requirements of the Race Equality Scheme. Third Assembly Update The checklist was produced as agreed and disseminated. There is little evidence to suggest that the checklist has been used by committees since its introduction which has largely been due to responding to the pressures associated with organisational change. The establishment of new committees in the Third Assembly is an ideal opportunity to re-issue and raise awareness of the checklist. The Equality of Opportunity Committee’s view will be sought on this. |
| Committee Clerks will use this checklist, in their discussions with Chairs on Forward Work Programmes and Agendas, to draw attention to the requirements of the Race Equality Scheme. | From April 2005 | Clerks to Subject Committees | See above. All Committee Strategic Forward Work Programmes were forwarded to the Equality of Opportunity secretariat and the issue was discussed during the Equality of Opportunity Committee meeting on 14 June 2006. |
| Committee Service will ensure that Subject Committees submit their strategic forward work programmes to the Equality of Opportunity Committee to assess whether they pay due regard to equality issues including race equality (in line with recommendation 26 of the Mainstreaming Equality report) | November 2005 and on-going annually | Clerks to Subject Committees and Equality of Opportunity Committee Clerk | Subject Committees’ Strategic Forward Work Programmes were forwarded to the Equality of Opportunity Committee (EOC) for consideration at its 14 June 2006 meeting. The Committee felt that consideration should be given to more in-depth scrutiny of the programmes in future years. Third Assembly Update The Committee might wish to consider how best to scrutinise the work of Scrutiny Committees as part of its broader remit. |
| In discussions with Members on committee business, Committee Clerks will draw attention to the requirements of the Race Equality Scheme as appropriate | From April 2005 | Clerks of Subject committees | There is little evidence to suggest that this has been taken forward but the Equalities Team can work with Committee Clerks to advise them of building race equality and other equality considerations into discussions concerning committee business. |
| Relevant race equality bodies will be included on a generic list of organisations to be consulted by Clerking teams for every policy review. The list will be reviewed annually with the Equality of Opportunity Committee Standing Invitees. Other relevant race equality bodies will also be included on the list of organisations to be consulted by Clerking teams for specific policy reviews. | April 2005 and annually thereafter | Equality of Opportunity Committee Clerk | Full list of consultees agreed by the Equality of Opportunity Committee during the Summer term 2005 and forwarded to Committee Service teams. A comprehensive single database has been developed jointly in the Committee Service. Third Assembly Update Consideration should be given to an update list being agreed by the Committee in the Third Assembly. |
| The Members' Research Service and Committee Service will ensure that minority ethnic representative bodies and communities are specifically targeted when gathering evidence to underpin committee policy reviews. The good practice guidance for policy reviews will be amended accordingly. | April 2005 | Equality of Opportunity Committee Clerk and MRS Team Leader for Social Justice | A link to the Equality Consultee list (which includes details of bodies representing minority ethnic people) is included in Chapter Six – Policy Development, Committee Service Manual. Committee Clerks to submit six-monthly reports for Head of Service. Third Assembly Update The revised guidance on scrutiny inquiries (for the Third Assembly) makes reference to the Equality Consultee list. There is no evidence to suggest that six-monthly reports have been submitted. Again, this has largely been due to responding to the pressures associated with organisational change. |
| Committee Service will ensure that minority ethnic representative bodies and communities are specifically targeted when formulating agendas, venues and speakers for regional committee meetings. Guidance for regional committees (section 4.4) will be amended accordingly as part of the review of the Handbook of Committee Procedure. | August 2005 | MRCS Central Co-ordination Unit. Regional Committee Clerks. | Third Assembly Update The Handbook of Committee Procedure has been re-written to make it more relevant and user-friendly for incoming Members to the Third Assembly. It also takes account of changes brought about by the Government of Wales Act 2006. |
| Committee Service will provide the secretariat to the Equality of Opportunity Committee and, in so doing, ensure that it is provided with the support it requires to fulfil its role of monitoring implementation of the Race Equality Scheme | Ongoing | Head of MRCS | Clerking team will work with the lead MRS researcher and Equality Development Officer to explore ways of streamlining and making more effective, arrangements for the Equality of Opportunity Committee to scrutinise the Assembly’s statutory equality reports. In the Second Assembly, all Subject Committees were invited to scrutinise the relevant Departmental section of the Welsh Assembly Government’s Seventh Equality Report and feed their views to the EOC. The views of Subject Committees helped inform the EOC scrutiny session on the Report at its 25 October 2006 meeting. |

| Function: Information and Advice | Classification: Medium |
| --- | --- |
| Objective: Greater awareness of minority ethnic issues amongst Assembly Members |
| Actions | Date | Lead | Performance Measures |
| The Members' Research Service will provide briefing to the Equality of Opportunity Committee to enable it to fulfil its role of monitoring implementation of the Race Equality Scheme by Ministers and other Committees. General guidance already provided to Members and specific briefing to be provided as appropriate for agenda items. | April 2005 and ongoing thereafter. | Equality of Opportunity Committee Clerk and Team Leader - Equality. | Briefing is provided to the Equality of Opportunity Committee for this purpose and has been offered to all subject Committees. Briefings include background information and suggested questions. The number of equality-specific briefings produced for subject Committees is beginning to increase, as is the inclusion of equality focused suggested questions into non-specific briefings. The equality development officer, MRS researchers, Clerking teams and Members will evaluate the impact of this in 2005-06. Third Assembly Update MRS will provide briefing to the EOC to support its scrutiny of the WAG Annual Equality Report in December 2007. MRS has provided a range of equality-focused briefings for the EOC and for individual Assembly Members through the confidential enquiry service. Some MRS briefing provided to Scrutiny Committees to support scrutiny of the 2007 Draft Budget has included suggested equality considerations, including some specifically relating to BME communities. |
| The Members' Research Service will invite the Chair of the Equality of Opportunity Committee to attend the Panel of Chairs at least once each year to discuss the handling of equality issues by subject committees. | By September 2005 and annually thereafter. | Head of MRCS | The Chair of the Equality of Opportunity Committee attends Panel of Chairs as an “Observer”. Equality of Opportunity has been included as an agenda item at Panel on a termly basis. On 29 November 2005, the Panel agreed to the suggestion of the Chair of the Equality of Opportunity Committee that subject Committees should each look at the relevant sections of WAG equality reports to ensure better scrutiny. Most Committees have discussed the 6th WAG Equality Report or made plans as to how they will undertake scrutiny in the future. The impact of this will be evaluated during 2006-07 so that the EOC Committee can consider developments and areas which still need further work when they next consider the Assembly’s 7th Annual Equality Report and RES for 2005-06 in the Autumn 2006. Third Assembly Update As the Panel of Chairs is no longer in existence, the Committee might wish to discuss how Scrutiny Committees might consider equality issues. |
| The Members' Research Service will, as part of its internal quality assurance process, assess the written briefing that it provides to individual Members and Committees for balance and appropriate consideration of equality issues. | Ongoing | Head of MRS | The MRS quality assessment tool which is used to check MRS outputs, includes questions which focus on the degree to which written outputs address issues of equality and discrimination. The number of equality-specific briefings produced for subject Committees is beginning to increase, as is the inclusion of equality-focused suggested questions into non-specific briefings. The impact of this will be evaluated in 2005-06 by the equality development officer, MRS researchers, Clerking teams and Members. Third Assembly Update A formal evaluation of the impact of equality considerations included in MRS briefings was not carried out due to pressures on staff resources during organisational change. The MRS Draft Service Plan for 2007-08 however includes a number of actions which should enable us to better assess the impact of our briefing. For example: Committee Member use of MRS briefings is already being logged; A log of feed back from individual Assembly Members is also kept; A Customer Liaison Group will be established to identify and co-ordinate further actions which should improve our ability to assess the needs of Assembly Members and the ways in which they use our briefings; Guidance will be produced to support researchers to better incorporate equality considerations into their briefings; and Every member of staff will have a performance objective to demonstrate how they are contributing to the goal of undertaking our work within a framework that promotes sustainability and equality of opportunity. |
| The Members' Research Service will ensure that one of its programme of awareness sessions for Members and their staff, is targeted at the implications of the Race Equality Scheme. | By April 2005. | Head of MRCS | Difficulties around session attendance has slowed down the programme. A RES session has not been held. Work has been undertaken by a group to better establish the needs of Members and Staff. A RES session will be held in 2006-07. Given the difficulties in arranging a session that Members are able to attend it was decided that this would not be an effective way of raising awareness. Written and verbal briefing was provided to the Deputy Presiding Officer, House Committee and EOC in 2006-07. Third Assembly Update Changes to the status of the Assembly, the Assembly Government and the establishment of the Assembly Commission have resulted in changes in responsibilities regarding the various statutory equality duties. We will identify the most effective ways of briefing Members and their staff on the various equality schemes. Colleagues in the Legal Services also have a role in this and briefing has been provided to the APS Executive Board on the application of current legislation to the Assembly and the Assembly Commission. MRS will produce a research paper for all Members and their staff, highlighting responsibilities and who they apply to by the end of 2007. |

| Function: Facilities and Services | Classification: Medium |
| --- | --- |
| Objectives: greater awareness of minority ethnic issues; provide a welcoming environment for visitors from minority ethnic communities; increase awareness of the work of the Assembly amongst minority ethnic groups; encourage all ethnic groups to participate in the work of the Assembly; encourage participation in the electoral system by all ethnic groups. |
| Actions | Date | Lead | Performance Measures |
| Research contacts and readership of ethnic minority publications in Wales. | By March 2006 | Head of Media Relations | Database produced December 2006. In March 2007, press releases targeting specialist BME press and media were sent to raise the profile of Commonwealth Day events. Third Assembly Update Contacts researched but proving difficult to access circulation figures. Work will continue during 2007/08. From April 2007, press releases targeting specialist BME press and media were sent regarding: Mohammad Asghar AM becoming the first Assembly Member from a BME background; and The launch of the Assembly Member Operation Blackvote Shadowing Scheme. |
| In consultation with the Communications Directorate, build a database of national press/media aimed at minority ethnic groups in order to target with appropriate press releases. | By March 2006 | Head of Media Relations | As above |
| Function: External Communications | Classification: Medium |
| Objectives: to promote good race relations and increase knowledge, participation and interest in the work of the National Assembly for Wales amongst people from minority ethnic communities; improve and increase voter participation among people from minority ethnic communities; improve the services provided to the public and increase awareness of those services to people from minority ethnic communities; work in partnership with community members from minority ethnic groups to increase participation, knowledge and interest in the work of the National Assembly for Wales; and improve interest in the work of the Assembly via live broadcasting amongst people from minority ethnic communities. |
| Actions | Date | Lead | Performance Measures |
| Carry out an equality and social inclusion review of the Exhibition and Visitor Centres to ascertain if the diverse culture of Wales is fully represented. | March 2006 | Marketing Manager | The Marketing Manager in consultation with the Access Co-ordinator carried out an equality and social inclusion review of the exhibition and Visitor Centres. Exhibition Panels are changed in line with alteration to the Ministerial Portfolios and changes to Assembly services and political landscape. The panels will take note of recommendations made by the Access Co-ordinator to ensure that the cultural diversity of Wales is represented as far as possible. Third Assembly Update The Visitor Centre remains in the North Wales; however a feasibility study is currently underway regarding the future use of the Pierhead Building. |
| Prepare tender documents for the refurbishment of the Assembly Exhibition centre to ensure that all exhibition panels are inclusive of all main ethnic groups in Wales. | By July 2007 | Marketing Manager, in consultation with Purchasing Unit | Exhibition panels are changed in line with alteration to the Ministerial Portfolios and changes to Assembly services and political landscape. The panels will take note of recommendations made by the Equalities and Access Adviser to ensure that the cultural diversity of Wales is represented as far as possible. Third Assembly Update The exhibition panels in the North Wales Visitor Centre have recently been updated to reflect the changes related to the Government of Wales Act 2006 and are inclusive of the main ethnic groups in Wales. Pictures used in publications are also inclusive of the main ethnic groups in Wales. |
| Ensure that Assembly publications and information provided by the service have due regard for equality of opportunity for people from minority ethnic communities. | February 2006 (and annually thereafter) | Marketing Manager | Each publication is amended as required and images and language is scrutinised to ensure social inclusion. In addition, ‘Your Guide to the Assembly’ is currently produced in eighteen languages and is available on the Internet. |
| Review the eighteen languages that ‘Your Guide to the Assembly’ is produced in, ensuring that they reflect the diverse ethnic community in Wales. | Autumn 2007 | Marketing Manager | Conduct research into the logic behind our selection of languages for multi-lingual translation of publications and update accordingly. Third Assembly Update This has not been carried out due to responding to the pressures associated with organisational change. This will be incorporated however in 2008 as part of an overall review of Assembly publications. |
| Monitor the distribution of publications and web-site take up of leaflets in minority ethnic languages. | Publish report by March 2006. Statistics will be collated quarterly. | Marketing Manager | The statistics for downloads of leaflets in minority ethnic languages are available but has proven to be problematic. It has not been possible to collate accurate figures to date but a solution is being sought from the IT provider. Third Assembly Update There is not the capability at present in the IT system to count the number of PDF downloads from the Internet site. We will take this into account as part of a wider review of our Internet site’s capability. |
| Provide, in partnership with Human Resources branch, specific training for all new and existing front-line staff on the duties and responsibilities contained within the Race Relations Act. In addition, cultural, race and religious awareness training will be delivered. | Some front-line staff will have received this training by August 2005. | Equalities and Access Adviser | Access and Equality Training has been devised and has been delivered by the Equalities and Access Adviser in partnership with Human Resources during 2006. The training includes all aspects of equality including cultural, race and religious awareness issues. The training has been independently evaluated. Continuous evaluation at each session has been very positive. The training is mandatory for all new staff as part of the induction programme. Existing staff are encouraged to attend. The take up has been very high and will continue to be rolled out during 2006-07. All ‘Welcome Host’ training involves an equality element. Third Assembly Update Training will be adjusted accordingly to correlate with the Single Equalities Scheme and Action Plan 2008. |
| Obtain customer feedback from under- represented groups on the front line services provided by APS. | By December 2005 | Equalities and Access Adviser | Efforts are made to obtain customer feedback. In 2006, the Equalities and Access Adviser has attended events, hosted in the Assembly and external events that are organised by under-represented groups. There have been no complaints or negative feedback received from under-represented groups and positive verbal feedback on the services the Assembly is directly responsible for have been good. Third Assembly Update Further work on this will commence in 2008. |
| Conduct or commission a feasibility study for an audio tour facility at the visitor and exhibition centres which would promote inclusivity and which would provide equal access for all. This would include an audio tour in minority languages used within Wales in addition to Welsh and English. | By October 2006 | Equalities and Access Adviser | Third Assembly Update The audio tour facility was discussed but set aside on grounds of cost, but we will review this in 2008 alongside the feasibility study for the Pierhead and review of Senedd access. |
| Promote the education visits programme to schools/colleges that have currently not visited the Assembly and that have a high number of minority ethnic pupils as identified from the research above. | By March 2007 | Education Team Manager | The Education Team has increased its weekly visits capacity in Cardiff. The resulting 19% increase in visitors in 2005-06 and 30% increase in visitors 2006-07 shows that the service is much more accessible to schools and as a result, pupil diversity is wider. Third Assembly Update Development of enhanced, accessible education facilities in the Assembly Office is underway. This is due for completion in early 2008. |
| Review all education visit-booking forms to ensure that cultural and religious requirements of visiting schools are considered as part of the planning process. | By March 2006 | Education Service Manager | Schools and colleges provide information on cultural or religious requirements during visits to the Assembly. Schools are asked if they have any requirements and their requirements are subsequently factored into the visit. |
| Identify and contact minority ethnic groups in Wales inviting them to have guided tours of the Assembly. | By March 2006 and annually thereafter | Visits Team Manager | Letters were sent inviting groups to visit the Assembly in June 2005. The take up has been limited but there has been a small increase. Third Assembly Update This exercise will be repeated in 2008. |
| Develop and maintain a data base of minority ethnic community groups and contacts within Wales in order to further promote the work of the Assembly. | By December 2005 and annually thereafter. | Visits Team Manager | Database of contacts established and maintained. This is reviewed on a quarterly basis and letters of invitation inviting groups to visit are sent out annually. Third Assembly Update To be reviewed in 2008. |
| Consider providing a direct link from the homepage to a new page, as part of the internet/intranet review project, which will bring together all available minority language material | By September 2007 | Head of ICT | Third Assembly Update This has now been completed. New site went live on 4 May 2007. |
| Investigate with the Members Research Service and Public Information and Education Branch, as part of the internet/intranet review project, an e-forum to collect information on the demand for minority language material on the website | By September 2007 | Head of ICT | Third Assembly Update The new website can facilitate e-forums and can be managed in-house. |
| Consider revising the Content Management System, as part of the internet/intranet review project, to include requirements for multi-language control and availability. | By September 2007 | Head of ICT | Third Assembly Update The Livelink CMS has the capability to do this but any development for languages other than Welsh and English will have to be costed. |
| Consider providing the tools and procedures to allow publication in minority language to the website as html documents, as part of the internet/intranet review project. | By September 2007 | Head of ICT | Third Assembly Update See above. |
| Set up a working group to consider the legal requirements of providing a language policy to take account of any responsibilities under the Race Relations (Amendment) Act. | By November 2005 | Equalities and Access Adviser in consultation with stakeholders | A working group has met three times since November 2005. The group has investigated good practice in similar organisations and discussed possible solutions with the Commission for Race Equality. Third Assembly Update Assembly Commission to consider and review the requirement for a language policy. |
| Ensure that call-off contract for written translation in minority ethnic languages is robust so as to provide professional service. | By Spring 2005 | External Communications Service | A call off contract is in place with three companies but take-up has been very low. We also offer a simultaneous telephone interpretation service which is a translation service in up to sixty languages for people whose first language is neither English nor Welsh. This service provides a telephone interpretation for individuals seeking public information about the Assembly and the services it provides. A simple phone call to the ‘Public Information Line’ identifying the language required and the call will be routed through an interpreter. There is no additional charge for this service and the calls are held in the strictest confidence. |
| Function: Human Resources | Classification: High |
| Objectives: promote good race relations; ensure fair treatment for people from all ethnic groups; and increase ethnic minority representation within the workforce. |
| Actions | Date | Lead | Performance Measures |
| Ensure that the training policy considers the Race Equality Scheme (RES) and provides opportunities for APS staff and Assembly Members to seek additional support where required. | Ongoing | Head of Learning and Development | Staff to identify training requirements in individual performance reviews (PMRs). Training Policy was reviewed in April 2005 and equality sections amended. Policy has been published on intranet. |
| Identify training and development needs of APS staff through PMRs, paying particular regard to the developmental needs of staff from a minority ethnic background | May 2005 - ongoing | Head of Learning and Development | This process is ongoing, utilising the annual Performance Management system. |
| Record and monitor ethnic background of staff applying for and/or receiving training. To analyse statistics for any inequalities. | Ongoing | Head of Learning and Development | Monitoring is ongoing through out year and issues dealt with as they arise. No issues have arisen. |
| Develop training for those members of staff who are responsible for the Race Equality Scheme and action planning process. | May 2005 | Head of Learning and Development | Training has been included as part of a wider contract for equality training for staff. Third Assembly Update The programme is now delivered through the new Assembly training provider (Elieshia Training) from April 2006 onwards. |
| Provide all APS staff with refresher training consisting of a series of short 1-2 hour sessions on various equality (including race) issues. Staff will be expected to select at least one session, relevant to their work from a ‘pick & mix menu’ | September 2005 | Head of Learning and Development | Training is delivered for all new starters and has also been rolled out for all front line staff. Courses for other staff have been designed and are available but are demand led. Equality is also incorporated into the Parliamentary Skills training programme. Third Assembly Update We are currently considering the most effective ways in which to continue to raise awareness about equality issues. |
| Monitor and review the new Induction training programme for all new staff and ensure that it raises awareness and enables staff to deliver elements of the Race Equality Scheme. | Late 2005 | Head of Learning and Development | Post-course evaluations have highly scored induction courses (all above our target rate of 8/10). The equality module of the induction has been revised to take account of emerging legislation. |
| Develop a training course for HR staff to improve their ability to provide advice and guidance on equality (including race) issues. | 2006 | Head of Learning and Development | Training which was delivered in April 2005 on discipline and grievance has included significant reference to race and other equality issues. Equality courses being run for all HR staff. |
| Write a regular article on issues relating to equality of opportunity (including racial equality) for APS newsletter | 2006/7 - ongoing | HR Equality Lead | Electronic APS newsletter started in April 2006. Articles referencing Race Equality to be included from July onwards. Third Assembly Update Equality articles are routinely included in editions of ‘The Slate’ to raise awareness amongst staff. |
| Monitor and review recruitment to APS for any possible discrimination and undertake further action if necessary | October 2005 | HR Equality Lead | Review of Recruitment completed in 2006. The Commission for Racial Equality’s code of recruitment was used during review and recommendations adopted. Third Assembly Update We are now considering engaging external consultants to recommend improvements to our recruitment processes to improve interest amongst the BME communities. We are also liaising with employers of best practice with the same objective. |
| Review the way that posts are advertised and develop improved mechanisms for promoting employment opportunities. | October 2005 | HR Equality Lead | Recruitment review completed. Cardiff South Enterprise centre (CSEC) used for promoting posts to ethnic minority groups. Advice taken from Chwarae Teg and Mewn Cymru with regards to female BME recruitment. |
| Develop an outreach programme for minority ethnic communities to raise awareness of APS recruitment procedures and competency framework. | June 2005 | HR Equality Lead | An outreach programme was launched in summer of 2005 and in the summer of 2006. Third Assembly Update HR colleagues continue to liaise with the voluntary sector to seek best practice advice. We are establishing paid secondment opportunities for people from the BME community. |
| Deliver the outreach programme above to minority ethnic communities to raise awareness of APS recruitment procedures and competency framework. | May 2005 | Head of Human Resources | Pilot outreach programme in partnership with Cardiff South Enterprise Centre (CSEC) to target groups and raise awareness of APS’s recruitment practices. Programme has been successful in recruiting three new members of staff from minority ethnic staff backgrounds. |
| Network with community organisations and groups to raise APS profile (using the partnership developed with CSEC) | May 2005 | Head of Human Resources | Network of contacts for future outreach programme partially established through council and job centre. Contacts to be extended (will also include other equality strands) by March 2006. Third Assembly Update We have liaised with Chwarae Teg and MEWN Cymru with regards to female BME recruitment. A secondment has been arranged with MEWN Cymru. |
| Target schools with a high proportion of students from a minority ethnic background, offer work placements and opportunities to shadow senior members of staff and Assembly Members. | Early 2006 | Head of Human Resources | Participation in the Cabinet Office Development Placement Scheme for students from Minority Ethnic backgrounds - one student undertook a summer placement in 2005 and another in 2006. Third Assembly Update Specific local schools have been targeted for placements in summer 2007. APS has also continued to offer work-placements to students and this has included three from minority ethnic backgrounds. |
| Evaluate the effectiveness of the outreach programme and make improvements where necessary | July 2006 | Head of Human Resources | Review of this scheme is ongoing. |
| Expand existing outreach networks via additional community organisations to raise APS profile | Early 2008 | HR Equality Lead | Will utilise visits by Public Information Team to promote our equality agenda. |
| Evaluate contact list of community organisations to ensure that outreach programme is reaching the right audience | 2007 | HR Equality Lead | HR outreach plans in place. |
| Assess the effectiveness of work experience programme | 2007 | HR Equality Lead | Ongoing monitoring. |
| Monitor all alleged race harassment incidents | Ongoing | Head of Human Resources | Monitoring is ongoing. One case has been raised in 2005-06 and has been dealt with in line with Assembly policy. |
| Implement a new “dignity at work” policy, and ensure that staff are aware of the policy | 2006/7 | Head of Human Resources | Third Assembly Update Policy was reviewed for administrative and legal separation between the Assembly Parliamentary Service and the Welsh Assembly Government prior to April 2007. |
| Assess the effectiveness of the policy | 2007 | Head of Human Resources | ‘I am treated with fairness and respect at work’ elicited a 79% favourable response in 2006 staff survey. |
| Promote use of U-Access (package on HR IT system) to provide accurate information on ethnicity which can be cross referenced with personnel practices such as training, internal recruitment and performance management | Ongoing | Head of Human Resources | Monitoring of recruitment and development continues. Staff have also been asked to refresh their equality monitoring information and this is being manually added to the HR IT system. This objective has been partially met and is due for completion by January 2008. Third Assembly Update The U-access (self-service module) is currently being revised and will be re-launched in early 2008. It will then include all equality strands including disability, sexual orientation and religion. Staff will be able to update their own information confidentially. |
| Prepare reports to senior management team indicating why staff are leaving, which can be broken down by ethnicity | 2006/7 | HR Equality Lead | Statistics are monitored on an ongoing basis. |